## INSTRUCTIONS
WORKBOOK INSTRUCTIONS
This workbook provides detailed to-do list templates in the format of a timeline for the various types of events that volunteers may host.
Starting a new Event Timeline |  | Using an Event Timeline
Step | Notes | Column | Notes / Instructions
1 | Open this workbook in your desktop Excel app | Timeline | Activities listed in all cells adjacent to a timestamp should fall within that timeline
2 | Select the tab that is appropriate for the type of event you are hosting | Task Status | Use the drop-down menus in the cells to select the status of the task
| TO MOVE YOUR TEMPLATE INTO A NEW WORBOOK: | Task Description | Read these descriptions to understand what needs to be done
3 | Right click on the tab name and select "Move or copy…" | Links to Resources | Any resources referenced in the Task Description (typically bolded) will be linked here
4 | Under "To book:", click the drop-down arrow and select "(new book)" (see screenshot) | People Assigned | • Type the names of the people into the appropriate cells
5 | Modify template according to your event - ex. add your scheduled social media posts, or divide the schedule into sections based on your event style |  | • If there is more than one person assigned to a task, separate the names with commas
6 | Save your new schedule to your computer and share with your team |  | • To see a filtered list of names, select the filter arrow and click on the conditions you would like to see
• To unfilter the list, select the filter arrow then "select all". If the spreadsheet is out of order, go to the "ORDER" column beside the "Assigned People" column and filter from smallest to largest
|  | ORDER | This column is used to indicate the original order of the tasks

## VIRTUAL
Event Name
Event Date |  | Region or Chapter
Event Time |  | Event Time Zone
Event Venue |  | Event Platform Link
TIMELINE | Task Status | Task Description | Links to Resources | People Assigned | ORDER
2 months before the event | FOCUS: Have initial discussions and consider important event questions. |  |  |  | 1
|  | Theme chosen: • Consider the purpose and outcomes of your event • Which of the 5 volunteer goals your event will meet? | Volunteer Hub -> Training |  | 2
|  | Has this event been done in the past? • If yes: reflect on the feedback and plan accordingly • If no: connect with the Alumni Relations Volunteer Engagement team to discuss the idea, budget, and resources |  |  | 3
|  | Time and date confirmed. Check that no holidays conflict with your event date. |  |  | 4
|  | Audience: • Who will attend the event? • What is the potential audience size? |  |  | 5
|  | Will the event be formal or informal? |  |  | 6
|  | Venue: Where will the event take place? Refer to the list of virtual venue options. | Event Planning Guide for Volunteers.pdf |  | 7
|  | Technical event details: • Will the event be live-streamed or pre-recorded? • Consider offering two registration options: attend the event live, or receive a recording after the event |  |  | 8
|  | Budget: Consider the costs associated with your event and prepare a budget. | Volunteer Event Budget.xlsx |  | 9
| FOCUS: Planning to move ahead with the event in a timely manner. |  |  |  | 10
|  | CRITICAL PATH CREATED: |  |  | 11
|  | • Important dates noted |  |  | 12
|  | • Volunteer roles defined |  |  | 13
|  | • Need for Alumni Relations staff support defined and communicated |  |  | 14
|  | • Technology test booked (1-2 days prior to the event date). The technology test meeting can also be the "Pre-Event" meeting for panelists |  |  | 15
|  | • Post-event debrief discussion booked (for within 1-2 weeks after the event) |  |  | 16
|  | If your event is in North America, discuss how a land acknowledgement can be incorporated with the Alumni Relations Volunteer Engagement team. |  |  | 17
|  | Confirm panelists. |  |  | 18
|  | Confirm moderator. |  |  | 19
|  | Confirm emcee. |  |  | 20
|  | Review the Event Request Form for the details required to submit an event. | Volunteer Event Request Form |  | 21
| FOCUS: Pull together discussions and submit the Event Request Form. |  |  |  | 22
|  | Will your event require a broadcast email to be sent out? If so, follow the Mass (Broadcast) Email Guide and include the appropriate details in your Event Request Form submission. | Mass (Broadcast) Email Guide.pdf |  | 23
|  | Fill out and submit the Event Request Form. | Volunteer Event Request Form |  | 24
|  | Sponsorship requests submitted. |  |  | 25
|  | Student engagement plans finalized. |  |  | 26
|  | Prizes and speaker gifts purchased. |  |  | 27
|  | Any branded elements ordered via Alumni Relations. |  |  | 28
1 month before the event | FOCUS: Event promotions. |  |  |  | 29
|  | Plan social media promotions: • Refer to the Social Media Guide to understand how to use your platforms effectively • Schedule regular posts about the event (before, during, and after) | Social Media Guide.pdf |  | 30
|  | Mass (broadcast) emails scheduled with Alumni Relations (3 weeks in advance of event): • 2 weeks out: first invite email • 1 week out: reminder email | Mass (Broadcast) Emails Guide.pdf |  | 31
|  | If you would like to have your event promoted over larger university networks, communicate with the Alumni Relations Volunteer Engagement team. |  |  | 32
|  | Co-op students invited. |  |  | 33
| FOCUS: Event implementation. |  |  |  | 34
|  | Prepare your Event Outline and share it with the Alumni Relations team. | Event Outline.docx |  | 35
|  | CREATE 2 EVENT SCHEDULES: |  |  | 36
|  | Schedule for attendees • Include key times and activities • If your event is more than 45 minutes long, plan breaks |  |  | 37
|  | Schedule for event team • Follow the schedule in your Event Outline • Assign day-of roles for the event team | Event Outline.docx |  | 38
|  | Review the event schedules with the event team. |  |  | 39
|  | Technology: • Have a technology test meeting with event team and key event people • Consider preparing a backup plan to refer to in the event of technological difficulties |  |  | 40
|  | Download Waterloo-branded video backgrounds for your event team to use. |  |  | 41
DAY OF | FOCUS: Deliver the event. |  |  |  | 42
|  | Follow the schedule in your Event Outline. | Event Outline.docx |  | 43
|  | Make notes of any feedback / insights for the post-event debrief throughout the event. |  |  | 44
|  | Follow-up communication: • Share a recording of the event • Post-event survey sent out within 24 hours of the event taking place |  |  | 45
1-2 weeks after the event | FOCUS: Post-event debrief. |  |  |  | 46
|  | Have an event debrief discussion with your event planning team. Discuss the high and low points of the entire process (before, during, and after the event) |  |  | 47
|  | Coordinate with the Alumni Relations Volunteer Engagement team to complete your Post-Event Debrief Summary. | Post-Event Debrief Summary.xlsx |  | 48

## IN-PERSON
Event Name
Event Date |  | Region or Chapter
Event Time |  | Event Time Zone
Event Venue |  | Event Platform or Website Link
TIMELINE | Task Status | Task Description | Links to Resources | People Assigned | ORDER
10 - 12 weeks before the event | FOCUS: Have initial discussions and consider important event questions. |  |  |  | 1
|  | Theme chosen: • Consider the purpose and outcomes of your event • Which of the 5 volunteer goals your event will meet? | Volunteer Hub -> Training |  | 2
|  | Has this event been done in the past? • If yes: reflect on the feedback and plan accordingly • If no: connect with the Alumni Relations Volunteer Engagement team to discuss the idea, budget, and resources |  |  | 3
|  | Time and date confirmed. Check that no holidays conflict with your event date. |  |  | 4
|  | Audience: • Who will attend the event? • What is the potential audience size? |  |  | 5
|  | Will the event be formal or informal? |  |  | 6
|  | VENUE: |  |  | 7
|  | Determine geographic location of event |  |  | 8
|  | Consider potential venues |  |  | 9
|  | Select the venue and sign the contract |  |  | 10
|  | Budget: consider the costs associated with your event and prepare a budget. | Volunteer Event Budget.xlsx |  | 11
| FOCUS: Planning to move ahead with the event in a timely manner. |  |  |  | 12
|  | CRITICAL PATH CREATED: |  |  | 13
|  | • Important dates noted |  |  | 14
|  | • Volunteer roles defined |  |  | 15
|  | • Need for Alumni Relations staff support defined and communicated |  |  | 16
|  | • "Pre-Event" meeting for panelists booked |  |  | 17
|  | • Post-event debrief discussion booked (for within 1-2 weeks after the event) |  |  | 18
|  | If your event is in North America, discuss how a land acknowledgement can be incorporated with the Alumni Relations Volunteer Engagement team. |  |  | 19
|  | Confirm panelists. |  |  | 20
|  | Confirm moderator. |  |  | 21
|  | Confirm emcee. |  |  | 22
|  | Review the Event Request Form for the details required to submit an event. | Volunteer Event Request Form |  | 23
10 weeks before the event | FOCUS: Pull together discussions and submit the Event Request Form. |  |  |  | 24
|  | Will your event require a broadcast email to be sent out? If so, follow the Mass (Broadcast) Email Guide and include the appropriate details in your Event Request Form submission. | Mass (Broadcast) Emails Guide.pdf |  | 25
|  | Fill out and submit the Event Request Form. | Volunteer Event Request Form |  | 26
|  | Catering vendor chosen and contract signed. |  |  | 27
|  | Sponsorship requests submitted. |  |  | 28
|  | Student engagement plans finalized. |  |  | 29
|  | Prizes and speaker gifts purchased. |  |  | 30
|  | Any branded elements ordered via Alumni Relations. |  |  | 31
4-6 weeks before the event | FOCUS: Event implementation. |  |  |  | 32
|  | Prepare your Event Outline and share it with the Alumni Relations team. | Event Outline.docx |  | 33
|  | CREATE 2 EVENT SCHEDULES: |  |  | 34
|  | Schedule for attendees • Include key times and activities • If your event is more than 45 minutes long, plan breaks |  |  | 35
|  | Schedule for event team • Follow the schedule in your Event Outline • Assign day-of roles for the event team | Event Outline.docx |  | 36
|  | Review the event schedules with the event team. |  |  | 37
|  | EVENT SUPPLIES: |  |  | 38
|  | Prepare a list of required event supplies. |  |  | 39
|  | Make plans to gather the event supplies. |  |  | 40
| FOCUS: Event promotions. |  |  |  | 41
|  | Plan social media promotions: • Refer to the Social Media Guide to understand how to use your platforms effectively • Schedule regular posts about the event (before, during, and after) | Social Media Guide.pdf |  | 42
|  | Mass (broadcast) emails scheduled with Alumni Relations (3 weeks in advance of event): • 2 weeks out: first invite email • 1 week out: reminder email | Mass (Broadcast) Emails Guide.pdf |  | 43
|  | If you would like to have your event promoted over larger university networks, communicate with the Alumni Relations Volunteer Engagement team. |  |  | 44
|  | Prepare your Event Outline. |  |  | 45
|  | Co-op students invited. |  |  | 46
DAY OF | FOCUS: Deliver the event. |  |  |  | 47
|  | Event setup. |  |  | 48
|  | Follow the schedule in your Event Outline. | Event Outline.docx |  | 49
|  | Make notes of any feedback / insights for the post-event debrief throughout the event. |  |  | 50
|  | Follow-up communication: • Share a recording of the event • Post-event survey sent out within 24 hours of the event taking place |  |  | 51
|  | Event takedown. |  |  | 52
1-2 weeks after the event | FOCUS: Post-event debrief. |  |  |  | 53
|  | Have an event debrief discussion with your event planning team. Discuss the high and low points of the entire process (before, during, and after the event) |  |  | 54
|  | Coordinate with the Alumni Relations Volunteer Engagement team to complete your Post-Event Debrief Summary. | Post-Event Debrief Summary.xlsx |  | 55