## Health PhD Planner
Faculty of Health PhD Thesis Defence Backwards Planning Tool
Information
Important dates calendar
PhD Thesis Examination Regulations
Desired Degree Completion Date (thesis accepted into UWSpace) | 2026-09-01
Count Type (Business/Calendar) | Business
Calculated Dates
Milestone | Date | Notes | Days from related date (editable)
Identify external examiner | 2026-05-09 | 12 weeks (recommended) prior to oral defence | 84
Supervisor submits PhD Proposed Thesis Examination Board form | 2026-06-06 | Minimum 8 weeks prior to oral defence | 56
Submit copies of thesis | 2026-06-27 | Minimum 5 weeks prior to oral defence | 35
Oral defence date | 2026-08-01 | Maximum 1 month prior to degree completion (based on decision of "accepted"; see notes for further information) | 31
Submit thesis to UWSpace for approval | 2026-08-18 | Recommended minimum of 1 week, but preferably 10 business days, prior to degree completion | 10
Formulas:
Date = B22-[Days from related date (editable)]
Date = [Date, row below]-[Days from related date (editable)]
As you start thinking about the end stages of your PhD, it is important to understand the processes and timelines related to the thesis defence, so that your degree completion is not delayed. This backwards planning tool will help you identify some of the major administrative tasks that need to be completed and assist you in establishing a realistic degree completion date.
There are general PhD Thesis Examination regulations that apply to all University of Waterloo PhD students, but there are some differences in administrative practices between the six faculties. As such, this backwards planning tool is designed specifically for PhD candidates in the Faculty of Health. If you have not already done so, take some time to review the PhD Thesis Examination regulations (link below) in addition to using this tool
Instructions:
- Enter a proposed degree completion date beside "Desired Degree Completion Date" (highlighted cell) and the proposed dates for other milestones will automatically populate in the cells below "Calculated Dates".
- When selecting your desired degree completion date, you may wish to consider planning a degree completion date around tuition refund deadlines or convocation deadlines. These dates can be found in the important dates calendar (link below).
- You can change the calculations to add more time in between milestones if desired (or less time, in the case of "maximum" timeframes) or to move dates off of weekends or holidays . You can do this by increasing (or decreasing) the number of days in the cells under "Days from related date". To reset to original values, use "undo" (Ctrl+Z) or download a new copy.
- Review the calculated dates with consideration for holidays or university closures, as outlined in the important dates calendar (the automatic calculation does not take these into account, and is based solely on calendar days or Monday-Friday for business day calculations)
Notes:
-Where the planning tool indicates minimum timeframes, early completion of these tasks is recommended. You may also need to add more days between milestones to account for holidays and university closures.
-Students should NOT be communicating with the external examiner prior to the defence. Talk to your supervisor to ensure this takes place in a timely manner.
-If the decision at an oral defence is ‘accepted’, students have a maximum of one month to complete revisions and have their thesis accepted into UWSpace. For more information on decisions and timelines, please see the PhD Thesis Examination Regulations.