“The process to build a robust employer-staff relationship requires a solid communication strategy, the successful integration of the key objective and Excellence Canada’s (EC) Progressive Excellence Program (PEP), and the ability to make prioritization decisions based on sound data.”

– University of Waterloo Strategic Plan, 2013

# Project Background & Overview – Excellence, Innovation and Wellness

The University of Waterloo has committed to the implementation of the Excellence Canada standard across campus as a national external framework which promotes organizational excellence, innovation and wellness.  The overarching goal of the campus-wide initiative is to help further the University’s Strategic Plan and eight strategic themes, particularly supporting the theme of a “robust employer/employee relationship.”  This initiative aligns well with the University’s foundational pillars as well as the Library’s four strategic directions, mission statement and values.

Excellence Canada’s Excellence, Innovation and Wellness (EIW) Standard provides a strategic umbrella for continual organizational improvement.  It is structured in a progressive implementation model with four levels (bronze, silver, gold and platinum) and is comprised of the following six drivers:

- Leadership and Governance

- Strategy and Planning

- Customer Experience

- People Engagement

- Process and Project Management

- Partners and Suppliers

The Library has been selected to pilot the introduction of the Excellence Canada standard.  The Library has a large, diverse cross-section of staff; in many ways, the Library can be seen as a microcosm of the campus employee community.  As well, the Library’s strategic directions align well with the campus Strategic Plan & eight themes.  The Library’s four strategic directions are in brief:

- Enabling student success

- Advancing research and scholarship

- News skills for new times

- New spaces for new times

The Library contributes to the achievement of the University's goals by collaborating with other members of the University community in teaching, research, learning and service. The Library’s current Mission Statement is focused on providing high quality, user-centric services and resources through the development and support of outstanding, knowledgeable, and empowered staff. The Library is committed to the following values:

- lifelong learning

- equitable access

- intellectual freedom

- confidentiality of access and records

- communication and cooperation

- continuous improvement

The Library’s short-term goal is to utilize the Excellence Canada Framework as a national standard to validate and build on the foundational work of the Library Review. Additionally, the Library will work with the campus to create a sample implementation pathway for bronze level certification. A key benefit will be the Library obtaining Bronze level certification to Excellence Canada’s Excellence, Innovation and Wellness Standard by November 2014.  At that point, the Library will review the process for the bronze level and determine how best to proceed with silver certification.

# Pilot Project Opportunities

- The Library as the pilot department will provide for:

  - Engagement with a large, diverse, and wide cross-section of employees for the process

  - Building on commitments and recommendations made in the Library Review Consultation Document, in connection with the Waterloo Strategic Plan & Themes

- Early adopter advantages include:

  - Campus & external support for the process

  - Benefits the campus community and prepares us for campus-wide implementation

  - Modelling organizational best practices in libraries and higher education

- Excellence Canada framework/standard enables the Library to:

  - Extend the work of the Library Review and further build our capability to realize our ambitions

  - Validate our organizational strength and effectiveness in the context of a national excellence framework

- Achieving Bronze certification will:

  - Be based on the engaged approach modelled in the Library Review

  - Recognize and further develop the Library as a rewarding, satisfying place to work

  - Inform our next steps of staff and service development in the Library

# Pilot Project Deliverables

A key project deliverable will be the Library’s Bronze Certification and associated processes and documentation developed to achieve the certification, including a staff communication & engagement plan. Internally, as per the Library Review, a key deliverable will be the enhancement of processes and development of a decision-making framework for multi-year planning and priorities setting. As well, the Library will have a solid foundation for Silver Certification.

In being the pilot site, the Library will have further deliverables to support continued campus implementation:

- Broad campus communication regarding the initiative and groundwork laid for future participants, including:

  - Presentation at May 2014 Executive Council retreat

  - Milestone reports to campus

  - Advantage taken of engagement opportunities, such as sharing results through the campus Communications Council, campus Leadership Forum and Staff Conference 2015

- Documentation to meet Bronze Level Requirements as well as samples and templates, such as

  - Documenting the process and lessons learned

  - Sample implementation path

  - Staff communication plan

# Pilot Project Governance Structure

Executive Sponsor - Geoff McBoyle, Vice-President Academic and Provost

Excellence Sponsor - Marilyn Thompson, Associate Provost, Human Resources

Excellence Leader - Mark Haslett, University Librarian

Pilot Project Steering Committee:

- Library Executive Committee

  - Mark Haslett, University Librarian (Excellence Leader)

  - Sharon Lamont, Director, Organizational Services

  - Pascal Calarco, Associate University Librarian, Research & Digital Discovery Services

  - Annie Bélanger, Associate University Librarian, Information Resources & Academic Excellence

- Annette Dandyk, Administrative Assistant

- Nancy Collins, Communications Librarian

- Marilyn Thompson, Associate Provost, Human Resources (Excellence Sponsor)

- Catherine Neville, Consultant & Coach, Excellence Canada

The formation and population of a Project Implementation Team and, if needed, any driver/theme teams will be dependent in part on the results of a baseline survey as well as the outcomes of a Gaps Analysis Retreat.

Key participants and stakeholders in the pilot will include:

- Library Executive Committee

- Library Managers Group

- Library Communications team support

- Driver leads and teams (Identification and population of any necessary driver teams will be considered after the baseline survey results have been reviewed and following the Gaps Analysis Retreat.  Where appropriate, non-Library representation will be considered.)

- A cross-section of Library staff (cross-level, cross-functional – replicating Library Review approach)

- University functional support as required

- Other specialists as required

Note:  By the very nature of this being a pilot project, the process will be evolving, iterative and engaged on numerous levels.

# Success Factors

The following factors at the University, Library, and Pilot Project Steering Committee levels will ensure the pilot’s success.

University

- Sponsorship and support of Vice-President Academic & Provost

- Investment in the Excellence Canada programme at the “Gold level”

- Engaged, pro-active support and participation from University Leadership and functional leads as required

- An identified campus priority in Waterloo’s new Strategic Plan is addressed

Library

- Seizing the opportunity to show leadership in measuring ourselves against external standards

- Approaching process excellence in a consistent manner to meet the needs of our internal and external stakeholders

- Maintaining momentum in efforts to address employee and employer benefits and impacts, particularly under the umbrella of “excellence, innovation and wellness”

- Sustaining and following through on the development and implementation of quality practices

- Validating and recognizing the Library’s organizational strengths and effectiveness

Pilot Project Steering Committee

- Demonstrating engaged participation by all members of the steering committee

- Ensuring appropriate stakeholder engagement

- Implementing effective and timely communication

- Providing sufficient time for employee engagement

- Setting achievable milestones

# Text boxes

Waterloo’s Eight Strategic Themes

- Experiential Education

- Entrepreneurship

- Transformational Research

- Outstanding Academic Programming

- Global Prominence & Internationalization

- Vibrant Student Experience

- Robust Employer-Employee Relationship

- Promoting a sound value system