## DRACI Chart
Activities will be highlighted if A and R are not assigned. Only one A should be assigned per row.
|  |  |  | D: | Make the decision; commit the organization to action
DRACI Chart |  |  |  | R: | Responsible for coordinating and/or doing the activity/work
|  |  |  | A: | Accountable for correct and thorough completion of deliverable; the approver, when applicable
|  |  |  | C: | Consulted with before/during the activity
|  |  |  | I: | Informed when the activity is completed
Project:
| Created/Updated: | 2023-03-02
| DESCRIPTION | Sponsor | Proj Mgr | Lead SMEs | Proj Team | Owner/Team Lead | BA | Governance (Steering) | Mgr PMO | Provost/ VPFA | Procurement | Change Mgr
project intake
| submit project proposal | A |  | C |  | R | R | I | C | D | I
| create business case | A |  | C |  | R | R | I
| business case approval | A | I | I |  | C | C | R | C/I | D
| proposal approval | A | I | I |  | C/I | C/I | R | C/I | D | I
project initiation
| create project charter | A/D | R | C | C/I | R | C | C/I | C/I |  | I
| identify & analyze stakeholders | A | R | C | C | R | R | C/I | I |  |  | C/I
| execute project kick off | A | R | C/I | C/I | C/I | C/I | I | C | I | I
project planning | bar: R R R
| commit resources ($, FTE) | A/D | R | C | C | C | C | R | C/I | D
| change management assessment |  | A/R |  | C/I | C/I | C/I | C/I | I |  |  | I
| create/execute communications plan | A | R | C/I | C/I | C/I | R | C/I | C/I |  |  | R
| create project mgt plan | A | R | C/I | C/I | C/I | C/I | C | C/I
| create change management plan | A: A; R: C/I |  |  | R
| create schedule | A | R | C/I | C/I | C/I | C/I | I | C/I
| create risk register | A | R | C/I | C/I | C/I | C/I | C/I | C/I
project execution & control | bar: C/I R
| manage requirements | C | A | C/I | C/I | C/I | R | I | I
| plan & execute training | C | A | C/I | C | C | R | I | C/I
| achieve project objectives | A | R | I | C | R | C | R | I
| ensure success of product/service | A | R | C | C | R | C | R | I
| obtain stakeholder engagement/buy in | A | R | I | C/I | R | R | R | I |  |  | R
| negotiate for project resources | A | R | C | C/I | R/C | C | C | C
| ensure quality assurance & control | C | A | C/I | R/C | R/C | R/C | I | C/I
| communicate project status | I | A/R | C/I | C/I | C/I | C/I | I | I
| oversee project team |  | A/R |  | C/I | C/I |  | I | C/I
| manage project risk | A | R | C/I | C/I | C/I | C/I | C/I | C/I
| manage project costs | A | R |  | C/I | C/I |  | C/I | I | D
| manage project change | A | R | C/I | C/I | C/I | C/I | R | C/I | I |  | R
| provide milestone sign offs | A | R | C/I | C/I | C/I | C/I | C/I | I
| manage standard project issues | C | A | C/I | R | R | C/I |  | I
| manage escalated project issues | A/D | R | C/I | C/I | R | C/I | R | C/I | I
| manage escalated project risks | A/D | R | C/I | C/I | R | C/I | R | C/I | I
| manage project scope | A | R | C/I | C/I | R | R/C | C/I | I
| report to governance bodies | A/R | R | I | I | R | C/I |  | I | A/D
project closure | bar: R R R
| provide final deliverable sign off | A | R | C/I | C/I | R/C | C/I | C/I | I | I
| determine project satisfaction/success | A | R | C/I | C/I | C/I | C/I | C/I | C/I | I |  | R/C
| add lessons learned to knowledge base | C/I | R | C/I | C/I | C/I | C/I | C/I | A
| create final close out report | C/I | A/R | C/I | C/I | C/I | C/I | C/I | C/I