## Instructions
Purpose of RAID Log
A RAID log is a simple, effective project/program management tool to organize a project/program by tracking risks, actions, issues, and decisions. The risk log records information such as triggers, probability, impact, mitigations, owner, et cetera for things that could go wrong but have not yet occurred. The actions log records information such as owner, due date, completion date, et cetera for things that need to be done. The issues log records information such as issue description, owner, resolution, et cetera for known problems that have occurred (if a risk triggers, it becomes an issue as well). The decision long records information such as decision description, date, who decision was made by for decisions made in the project/program.
The right level of detail needs to be determined for the RAID log, dependent upon the project/program so that it is an effective tool for audits, governance, and oversight of the project/program. It is a dynamic document that is constantly maintained throughout the project/program.
RAID Log Participants and Audience
Input into the RAID will come from many sources such as project documentation (charter, business case, intake form, meeting minutes, et cetera), sponsor, project team members, and other stakeholders. Another valuable source would be documentation from other projects that may be similar in nature (risks, issues, lessons learned, et cetera).
The author and maintainer is often the Program/Project Manager. Sometimes others may be providing updates, especially to the issues log. The Project/Program Manager will have to create a process for ensuring the RAID log is kept up to date and proper versioning occurs based upon the requirements of their project/program. Some Project/Program Managers prefer to be the sole author, and some allow others to update. Some Project/Program Managers may use others tools such as ACE Project or RT as their issues log and just use this document for risks, actions, and decisions.
Instructions
Risks:
1. Collect risks by asking yourself and others what may go wrong, and what would be the trigger. There is also a list of risk eliciting techniques available on the PMG website.
2. Assess probability and seriousness if the risk should occur. Grade the risk, using the chart under Definitions & Values.
3. Evaluate the risks according to the University’s and other stakeholder’s risk appetite.
4. Address risks by assigning risk responses and identifying the individual who will be responsible for taking action and monitoring the results.
4. Continuously review, monitor and update risks and mitigations.
Actions:
1. Add program/project action items to action log, according to the level of detail required for project/program and assign an owner.
2. Monitor action items continuously, and provide updates on status and when it is closed.
Issues:
1. Add issues as they arise to the issues log, according to the level of detail required for project/pogram and assign an owner.
2. Monitor issues continuously, and provide updates (on a recurrence cycle predetermined for project/program) on status and resolution.
Decisions:
1. Add decisions as the arise to the decision log, according to the level of detail required for project/program, with justification on why the decision was made.
Green italic text rows provide an example. This row can be deleted.
File in document repository.
Next Steps
Continously monitor and update the RAID throughout the project according to predetermined project/program management plans. During project closure, outstanding issues and risks should be communication during transition to operations. Decision information should also be shared during the transition to operations.

## Actions
ACTIONS
Item (#) | Description (Freeform) | Raised by (Name) | Owner (Name) | Raised (MM-DD-YYYY) | Days open (# Days) | Original Target (MM-DD-YYYY) | Current Target (MM-DD-YYYY) | Status Update (MM-DD-YYYY: Update) | Date Completed (MM-DD-YYYY) | Status (Open / Closed)
1 | Schedule working group sessions with Hiring Managers for new process to create job openings | Mary May, Project Owner | Joe Blow, HR Recruiter | 1991-03-25 | 97 | 1991-05-14 | 1991-06-30 | 1991-9-3: First working group session complete where hiring managers reviewed new process and user interface design | 1991-06-30 | Open
2
Formulas:
Days open (# Days) = IF([Date Completed (MM-DD-YYYY)]="",TODAY()-[Raised (MM-DD-YYYY)],[Date Completed (MM-DD-YYYY)]-[Raised (MM-DD-YYYY)])
Days open (# Days) = IF([Raised (MM-DD-YYYY)]="","",TODAY()-[Raised (MM-DD-YYYY)])

## Issues
ISSUES
Item (#) | Description (Freeform) | Impact (Freeform) | Raised by (Name) | Owner (Name) | Raised (MM-DD-YYYY) | Days open (# Days) | Original Target (MM-DD-YYYY) | Current Target (MM-DD-YYYY) | Status Update (MM-DD-YYYY: Update) | Status (Open / Closed) | Date Resolved (MM-DD-YYYY) | Resolution
1 | Job opening approvals won't execute when opening is created | can't automate approvals | Joe Blow | Jane Doe | 1991-07-02 | 80 | 1991-07-31 | 1991-08-31 | 1991-7-20: have determined there is a vendor bug in approval workflow. Awaiting vendor solution. | Closed | 1991-09-20 | Vendor solution provided. Approvals reconfigured to reflect new vendor code.
2
Formulas:
Days open (# Days) = IF([Date Resolved (MM-DD-YYYY)]="",TODAY()-[Date Resolved (MM-DD-YYYY)],[Date Resolved (MM-DD-YYYY)]-[Raised (MM-DD-YYYY)])
Days open (# Days) = IF([Raised (MM-DD-YYYY)]="","",TODAY()-[Raised (MM-DD-YYYY)])

## Decisions
DECISIONS
Item (#) | Decision (Freeform) | Justification for Decision | Decided by (Name 1, Name 2, ...) | Date (YYYY-MM-DD)
1 | Hiring Managers will be allowed a 3 month window after go live to submit job openings on forms to be handled manually. The recruiters will then enter the job opening information into the automated process. After 3 months, no paper forms will be accepted and all Hiring Managers must use the new automated process. | Hiring Managers will be included and have opportunities to provide feedback into new automated process to increase likelihood of acceptance. Manual paperwork window is short to allow them to adapt to the change, but also allow the University to begin using the new automated hiring process before a large number of employee retirements are expected. Recruiters will ensure manually submitted job openings are entered into the automated process so that applicants are presented with a consistent view of all job openings. | Recruitment Project Steering Committee: name 1, name 2, name 3 | 1991-10-15
2

## Definitions & Values
Risk rating
Impact | Probability
Very High | Very High
High | High
Medium | Medium
Low | Low
Very Low | Very Low
Probability | Impact
| very low | low | medium | high | very high
very low | Very Low | Low | Low | Medium | High
low | Low | Low | Medium | Medium | High
medium | Low | Medium | Medium | High | High
high | Medium | Medium | High | High | Very High
very high | High | High | High | Very High | Very High
Risk management planning, monitoring and reporting requirements
Risk Appetite | Risk Rating | Required Action
High Moderate Low | Very High | Ensure the project's sponsor or governace is aware of risk and agrees with the plan to manage risk. If the risk has an institutional impact, ensure this is communicated so that the risk can be further escalated. In addition, speak to your director about the escalation plan to track and keep abreast of decisions that may affect the project.
Moderate Low | High | Ensure the project's sponsor or governance is aware of risk and agrees with the plan to manage risk. If the risk has an institutional impact, ensure this is communicated so that the risk can be further escalated. Track when the risk is escalated.
Low | Medium | Report the risk up to the project’s sponsor or governance team to determine if the management plan for the risk is acceptable.
N/A | Low Very Low | Requires no attention above routine practices and procedures, and monitoring.

## Risk Chart (hidden)
Probability | Impact | Urgency
High | High | High
High | Low | Medium
High | Medium | High
High | Very High | Very High
High | Very Low | Medium
Low | High | Medium
Low | Low | Low
Low | Medium | Medium
Low | Very High | High
Low | Very Low | Low
Medium | High | High
Medium | Low | Medium
Medium | Medium | Medium
Medium | Very High | High
Medium | Very Low | Low
Very High | High | Very High
Very High | Low | High
Very High | Medium | High
Very High | Very High | Very High
Very High | Very Low | High
Very Low | High | Medium
Very Low | Low | Low
Very Low | Medium | Low
Very Low | Very High | High
Very Low | Very Low | Very Low