## Instructions
Instructions
Purpose of Stakeholder Register
The purpose of the stakeholder[1] register is to document who is impacted by the project/program, and their influence and impact on the project/program. This document will become an important tool towards project/program planning, team forming and developing, defining success criteria, communications, governance, and defining tasks and responsibilities. A complete stakeholder register that is created early in the project/program and monitored throughout increases the likelihood of success by ensuring appropriate stakeholder engagement.
Stakeholder Register Participants and Approvers
Input into the stakeholder register may come from many different sources including, but not limited to, Sponsor, senior leadership, project/program intake form and/or business case, charter, analysis/research, subject matter experts within business unit(s), and interaction with other stakeholders. The author is the Project Manager (or Program Manager) for the project/program. The stakeholder register should be reviewed by the Team, Sponsor, Business Analyst, and Owner for completeness and accurateness.
Instructions
The Project/Program Manager can begin filling out this document during initiation with a high level list of stakeholders and any information that may be known at the time. This is important towards ensuring the proper group of people are invited to the kickoff meeting. During Planning and Execution, more detail will be added to this document.
1. Research and understand stakeholders by reading any prior documentation and speaking to the sponsor and other stakeholders
2. Complete the stakeholder register with input from applicable stakeholders and the sponsor. Green instructional text can be removed from the document.
3. Review stakeholder register with applicable stakeholders for accuracy and completeness
4. Upload to the Knowledge Base
5. Continuously review the Stakeholder Register throughout execution for any changes in stakeholder influence or impact, especially if there are changes in scope or requirements
Next Steps
Once a preliminary list of stakeholders is identified during initiation (and the charter is approved), the kickoff meeting can be scheduled. The list of stakeholders will be used to ensure the appropriate people or groups are contacted and are part of the team forming process and kickoff. During planning, further details concerning influence and impact will be added to this document. This document will then be used to create the project/program management plan, schedule, communications plan, etc. Continue monitoring the stakeholder register throughout execution for any changes.
[1] A Stakeholder is a person or organization directly or indirectly involved in the project/program. The stakeholder may be positively or negatively affected and may or may not influence the project/program.

## Stakeholder Grid
Stakeholder Grid
Various models exist for developing a stakeholder management strategy. Using an influence vs impact grid has generally been a preferred approach as it is quick and effective. A Stakeholder’s position on the grid shows the type of player (category) the stakeholder is for the project/program and actions. It may be helpful to add stakeholders directly to the grid for a visual representation tool. Note: the information contained in this document can be very sensitive and meant for limited circulation only. Exercise caution in who this document is sent to and how it is published.
Key Player - High impact, high Influence: these are the stakeholders that must be fully engaged, and make the greatest efforts to satisfy. Important Player - High impact, low Influence: put enough work in with these stakeholders to keep them satisfied, but not so much that they become bored with your message. Affected Player - Low impact, high Influence: keep these stakeholders adequately informed, and talk to them to ensure that no major issues are arising. These stakeholders can often be very helpful with the detail of your project. Potential Player - Low impact, low Influence: again, monitor these stakeholders, but do not bore them with excessive communication.
Key Players (Manage Closely)
Important Players (Keep Satisfied)
Affected Players (Keep Informed)
Potential Players (Monitor for Change)
High
Low
High
Low
Influence
Impact

## Stakeholder Register
| # | Name | Department / Accountability | Title | Phase 3 Team Assignment | Project Role | Expectations | Project Influence | Project Impact | Stakeholder Category
| 1 | John Smith | IST | Manager, Operations | Sponsor | Team Member | Project to fulfill Business Case objectives: process efficiencies, improved compliance, security, reporting, integration and collaboration | High | High | Key Player
(manage closely)
2
3
4
5
6
7
8
9
10
11
12
13
14
15
16
17
18
Campus Partners | 19
20
21
22
23
24
25
26
27
28
29
30
31
32
33
34
35
36
37
38
39
40
41
42
DO NOT TYPE BELOW THIS LINE
Change Champion Team
Coordinating Team
HoME
Launch
Support & Training Team
n/a
Integration
Multiple Teams
TBD
Other