## Slide 1: Web accessibility compliance project
Presented to Web Advisory – February 19, 2014

## Slide 2: Project overview
GOAL
Develop a framework for long-term, sustainable support of web accessibility at the University of Waterloo.
  The intent is to build the capacity to be compliant into the organization, NOT to make all of our websites 100% compliant.

## Slide 3: Project Objectives
Summary of objectives:
Define and draft institutional statement for governance and compliance
Training and support plan for 2000+ web maintainers
Develop and hire expertise in web-accessibility to support the plan
Procure services in web-accessibility where required
Draft and implement a University wide communications plan on requirements and related support
Specify and implement procurement requirements for external web-service providers
Define and implement a website accessibility audit process
Draft recommendations for archival content (predating Jan 1, 2012)
Contact peer institutions regarding their planning
* Detailed description of scope for objectives available in the project charter: link

## Slide 4: Project Timeline & Strategy
Start date: February 2014
Phase 1 (Planning and research) projected completion: April 2014
Web Accessibility Compliance Project Management Plan
Web Accessibility Compliance Communications Plan (Objective #5).
Report from survey of peer institutions’ compliance efforts (Objective #7)
Statements of Work for remaining objectives.
Phase 2 (Delivery) projected completion defined in Phase 1

## Slide 5: Project Status
Sponsors: Chris Read and Dave Wallace
  Presented to Executive Council – February 5th
  Awaiting final approval of charter
Kickoff meeting with project group including steering committee – February 24th
  Define terms of reference for Steering Committee.
  Define terms of reference and expected time commitments for team members.
Stakeholders and Communication
  Web Steering – February 13th
  Web Advisory – February 19th
  Full project communications plan in progress

## Slide 6: Questions?
Ongoing accessibility support:
Liam Morland
lkmorland@uwaterloo.ca
About the project:
Jonathan Woodcock
jonathan.woodcock@uwaterloo.ca